Regulated Product Submission Standard Release 2

Project Plan

Version: 0.04

TABLE OF CONTENTS

1.0	Revision History	1

2.0	Project Overview / Description	1

2.1	Project Objectives	1

2.1.1	Overview	1

2.1.2	The mandate of the project	2

2.2	Completion and Success Criteria:	2

3.0	Project Goals	3

4.0	Project Scope	3

4.1	Scope Inclusions	3

4.2	Scope Exclusions	3

5.0	Project Deliverables	3

6.0	Project Stakeholders, Participants, Governance and Structure	4

6.1	Governance	4

6.2	Project Management Team	4

6.3	Advisory Committee	5

6.4	Domain Analysis Team	6

6.5	Specification Design Team (HL7 Development Team)	7

6.6	Testing Team	8

7.0	Project Risks	9

8.0	Communications	9

9.0	Project Milestones	10

10.0	Workgroup Engagement	11

11.0	Project Controls	11

11.1.1	Project schedule (high level work plan)	11

11.1.2	Project status reporting	11

11.1.3	Project Change Management	11

11.1.4	Project Issue Management	12

# Revision History

| File Name |  |
| --- | --- |
| Version | Date | Author | Description |
| 0.01 | 2008-02-28 | Peggy Leizear, Jason Rock | Initial draft |
| 0.02 | 2008-05-05 | Peggy Leizear, Jason Rock, Bill Rosen, Mary Ann Slack, Armando Oliva | Initial comments and edits completed |
| 0.03 | 2008-08-13 | Peggy Leizear, RCRIM Workgroup | Updated to include new information in the plan utilizing the original project charter |
| 0.04 | 2008-09-12 | Peggy Leizear, RCRIM Workgroup | Updated to include comments from workgroup and to include project schedule, risks, links to documents on the HL7 wiki |

# Project Overview / Description

## Project Objectives

### Overview

The RPS Release 2 project goal is to extend the existing HL7 V3 Regulated Product Submission Standard Release 1 with new requirements.  The project will enhance the existing RPS Release 1 standard ultimately intended to yield a global standard.

The intent of this project is to develop RPS Release 2, producing an HL7 standard that will support these objectives:

- New requirements for regulatory submissions to FDA described in the PDUFA IV Goals Letter, http://www.fda.gov/oc/pdufa/default.htm

- International requirements for eCTD v4 for drug and biologic products, and

- Use in global Medical Device electronic application submissions.

Development will be broken down into several “iterations”, i.e. time segments, during which a controlled amount of new functionality will be added to the current standard.

The initial phase will address new requirements to use RPS to prepare and submit regulatory submissions to the US FDA, specifically those related to new FDA PDUFA IV commitments. It is hoped that ICH eCTD v4 requirements will enter the work stream in the necessary timeframe merging all requirements into a single initiative.  If ICH and international device regulatory agencies are not able to deliver their requirements within the given time constraints, choose not to participate for any reason, or if HL7 is not able to complete a harmonised standard by early 2011, then the work done to support submissions to the FDA should proceed directly to normative ballot and a second phase of work will be required to include additional requirements.  This will follow at a later date as a new release.  Note all decisions are made based on HL7 policies and procedures (www.hl7.org) and other references made in this document.

### The mandate of the project

The first phase of this project will deliver new functionality to RPS, including responses to submission (two-way communications), navigational references, additional descriptive information about a submission (e.g. information currently collected on application forms) and ICH and Global Medical Device requirements if time permits.  The primary use case for this project can be described as follows:  sending regulated product information to a recipient (e.g. a regulatory authority or business partner), sending information back to the original sender, and using application information to report data about the submission. The role pairs participating in this transaction include:

- A sponsor submitting to a regulatory authority,

- A regulatory authority corresponding with a sponsor

- Transfers of information between regulatory authorities (e.g. submission of a device containing a drug where the EU Notified Body sends data to a competent authority for review).

The first phase of RPS Release 2 development will include: (could change based on progress of the project)

- Two-way communication

  - Any communication between sponsor and health authority relating to a specific submission of regulated product information, other than the submission content itself.  This includes (but is not limited to): requests for additional information, meeting minutes, general correspondence, pre-submission information, action letters, questions to and from the sponsor.

  - Communication between regulatory authorities relating to a specific submission of regulated product information.  This includes communication necessary in collaborative review of combination products.

- Referencing

  - Providing direct reference/navigation to other documentation (within a submission or to an external source) from a primary navigational structure (e.g from backbone/TOC) to master Files, other submission/application information, pre-submission information, etc.

  - Hyperlink content to other content

  - Providing direct reference/navigation from within a section of a submission document to another section (within the same submission)

- Providing information about the submission (e.g. metadata, information currently collected on application forms), including:

  - Information about the product

  - Contact information

  - Manufacturing site

  - Reuse, if applicable, metadata from other RCRIM and relevant HL7 domain standards.

- Support for work by ICH, GHTF, international device regulators and the ISO/CEN/HL7 Joint Initiative.

## Completion and Success Criteria:

We will have reached completion and success of RPS Release 2, Phase 1 when the RPS message standard:

- Is deemed capable of carrying regulatory correspondence from sponsor to health authority, and from health authority to sponsor.

- Is deemed capable of supporting a regulatory submission and review environment for varied submission types and their supplements that enables the following functions and supports the life cycle of the products

  - Electronic submissions received by a regulatory authority can be archived to enable retrieval through standardized automated links;

  - Electronic submissions can include cross-references to previously submitted electronic materials through standardized automated links; and

  - RPS can be applicable to human drugs and biologics, medical devices, foods, and animal health products.

- When project deliverables have been reviewed by the RCRIM RPS2 Workgroup

- When project risks have been mitigated or a contingency action has been implemented

- When negative ballots have been reconciled and the outcomes have passed ballot

# Project Goals

Goals:  The RPS Release 2 project goal is to extend the existing HL7 V3 Regulated Product Submission message (aka RPS Release 1) with new requirements.  The project will enhance the existing RPS Release 1 standard ultimately intended to yield a global standard.   Reaching this goals meets the FDA Amendments Act of 2007 (FDAAA) http://www.fda.gov/oc/initiatives/advance/fdaaa.html strategic imperative, and to include functionality identified as being within scope of the Release 2, Phase 1 initiative.

# Project Scope

## Scope Inclusions

RPS Release 2 will include:

- Regulatory submissions from sponsor (or sponsor’s agent) to regulatory authority

- Correspondence to and from either sponsor or regulatory authority

- Correspondence between regulatory authorities

## Scope Exclusions

RPS Release 2 will NOT include:

- Communication from sponsors to third parties, e.g.  contract research organizations.

- Enhancements to the PDF standard

- Transmission protocols (secure gateway, FTP, etc.)

# Project Deliverables

| Area | Deliverables |
| --- | --- |
| Project Management | Project Plan |
|  | Project Schedule |
|  | Risk/Issues/Change Management Logs |
| Domain Analysis | Storyboards |
|  | Use Cases |
|  | Activity Diagrams |
|  | Static Diagram and BRIDG Model Contributions |
| Development/Design Specification | State Diagram (status code) |
|  | Interaction Diagram (cause for sending) |
|  | RMIM |
| Testing | Test Plan |

# Project Stakeholders, Participants, Governance and Structure

The project stakeholders are:  Regulated Industry, Vendors, Regulatory Authorities, and Third Parties as it relates to drugs, biologics, medical devices, veterinary medicine, and food and feed products.

## Governance

The RPS Release 2 project will be governed in accordance with the bylaws and procedures of Health Level 7. These bylaws and procedures can be found at

http://www.hl7.org/documentcenter/public/bylaws/Bylaws_2008.pdf

These are based on the following roles:

Project Sponsor – FDA

Project Co-sponsor – PhRMA

Project Facilitator – FDA Responsible Party – FDA

Workgroup – RCRIM

## Project Management Team

The Project Management Team members actively direct & support primary project activities. Project-impacting decisions are made by the Project Facilitator, Sponsor and Co-Sponsor, in consultation with the Project Management Team and with advice and input of the Advisory Committee (below). All activities, progress and decisions will be communicated to the RCRIM RPS2 workgroup at large.

The Project Management Team consists of the following members:

| Name | Organisation | Role |
| --- | --- | --- |
| Peggy Leizear | FDA | Project Facilitator |
| Mary Ann Slack | FDA | FDA Sponsor |
| Bob Birmingham | J&J on behalf of PhRMA | PhRMA Co-Sponsor |
| Jason Rock | GlobalSubmit | HL7 Development Facilitator |
| Marti Velezis | BAH | Requirements Facilitator |
| Dirk Beth | Mission 3 Inc. | Testing Facilitator |
| Karin Sailor | MedTronic | Planning support |
| Terri Booth-Genthe | Wyeth | Planning support |

## Advisory Committee

The Advisory Committee consists of representatives from Health Authorities and Industry with expertise in varied regulated areas such as veterinary medicines, human therapeutics, nutritional supplements, etc. and an understanding of electronic submission standards, who are willing to participate in the RPS2 project. The Project Advisory Committee’s primary role is to provide a forum where stakeholder concerns can be raised and vetted as they relate to the overall direction and to review deliverables of from the RPS 2 sub-teams to ensure that the business requirements are being included and there are no obvious gaps in the requirements and review project deliverables.

The Advisory Committee will:

- Provide a forum for stakeholder representatives to meet and review progress of the RPS project

- Provide a forum for stakeholders to raise and address issues

- Advise the RPS Project Management Team

- Serve solely as an advisory group and will have no decision-making authority

In more detail, the Advisory Committee will:

- Consult on matters of:

  - Project direction changes

  - Representation on the Advisory Committee and the Project

  - Completion of key deliverables

- Advise on matters of:

  - Regional procedures and concerns

  - Communication plan

- Assist in:

  - Encouraging active participation in all stages of the project

  - Issue resolution

The following stakeholder groups will comprise the RPS Advisory Committee:

| (Suggested) Representative | Stakeholder/Affiliation | Domain |
| --- | --- | --- |
| Peggy Leizear | FDA | RPS 2 Project Manager |
| Mary Ann Slack | FDA | US Regulatory/Chair |
| Bob Birmingham | J & J | US Pharmaceutical Industry/CoChair |
|  |  | EU Regulatory (EFPIA) |
|  |  | EU Regulatory (competent authorities) |
| Geoff Williams | Roche and EFPIA | EU Pharmaceutical Industry (EFPIA) |
| Yasuhiro Araki |  | Japan Regulatory |
| Louis Boulay |  | Canada Regulatory |
|  |  | Device Regulatory European Notified Body Rep. |
| Bernie Liebler | AdvaMed | Device Regulated Industry |
|  |  | Foods |
|  |  | Veterinary Regulatory |
|  |  | Veterinary Regulated Industry |
| Andrew Marr | GSK |  |
| Chris Whalley | Life Sciences Oncology | Volunteer via Dirk for Device Regulatory Industry |

## Domain Analysis Team

The Domain Analysis Team is responsible for developing the requirements of Regulated Product Submissions Release 2.  Each of the stakeholders will bring their requirements for each of the RPS R2 scope areas, (two-way communication, referencing and information about the submission).  The RCRIM RPS 2 workgroup provides their requirements in order for the requirements facilitator and modeller to capture in a domain analysis model and artifacts.

The goal of the domain analysis team is to complete the domain analysis activities and artifact development necessary to establish the requirements for the HL7 Regulated Product Submissions Release 2.  The domain analysis documentation includes, but is not limited to:

  - Storyboards

  - Use Cases

  - Activity Diagrams

  - Static Diagram

  - Sequence Diagrams

During the course of the project, there will be a continuous requirements gather and/or refinement of requirements through an iterative, incremental process.  The BRIDG Model will be used as a starting point for the RPS Release 2 message.  In addition, the domain analysis process will incorporate the usage of the BRIDG model.  When appropriate the project team will be informed about the use of the existing data classes within BRIDG and when new data classes need to be added as the project progressing in an iterative, incremental fashion.

Participation within the domain analysis team can be achieved in the following manners:

- Domain Analysis subgroup discussions, as scheduled

- Discussion Boards on the HL7 RPS Release 2 Wiki (http://wiki.hl7.org/index.php?title=RPS_R2_Project)

- Face to Face and HL7 Working Group Meetings.

The Domain Analysis Team consists of the following members:

| Name | Role |
| --- | --- |
| Marti Velezis | Requirements Facilitator |
| Ben Schoenbrun | UML Modeler |
| Joel Finkle |  |
| Andrew Marr |  |
| Fred Miller |  |
| Ken Vanluvanee |  |
| Cynthia Piccirillo |  |
| Teresa Booth-Genthe |  |
| Terry Hardin |  |
| Karin Sailor |  |
| Taku Watanabe |  |
| Joerg Schnitzler |  |
| FDA |  |

The membership is open to the public.

## Specification Design Team (HL7 Development Team)

The requirements specification and any mappings to reference models are input to the specification design and packaging process. Existing specifications from earlier or concurrent design activities are also input to this process. The result from this process is a set of one or more of the following artifacts:

• Information Models

• Dynamic Models

• Functional Models

• Vocabulary Specifications

The artifacts produced during this specification design process are intended to be balloted as standards (e.g. informative, normative, and draft for trial use) however some projects may simply publish their artifacts as reference specifications.

Some specifications are produced as further refinements or derivative works based upon earlier design specifications. All specifications are produced in response to requirement specifications and make use of the HL7 reference models and earlier design work.

| Name | Role |
| --- | --- |
| Jason Rock | Lead |
| Joel Finkle |  |
| Fred Miller |  |
| David Donohue |  |

The membership is open to the public.

## Testing Team

The Testing Team will independently create and execute test scenarios (cases) to support the development phase of RPS Release 2, so as to verify the intended functionality of RPS and to provide necessary feedback to the specification design team prior to ballot. A primary goal of the testing team will be to support the development of RPS Release 2, where development will be broken down into several “iterations”, i.e. time segments, during which a controlled amount of new functionality will be added to the RPS spec during a development iteration, after which this specific new functionality will be the focus of the testing iteration.

A secondary goal of the testing team will be to lessen the magnitude of the more comprehensive end-to-end testing required during the DSTU phase of the project.  By establishing the testing practice early, participants will likely become more familiar and comfortable with the standard and the tools so that they will be better prepared for the larger testing initiative during DSTU.

The testing committees’ goal is to discover and communicate problems with the standard that could adversely impact its value. The testing committee must understand the context for the project and help others make informed decisions based on this context. Accordingly, the testing committee will evaluate the requirements and models and determine if they are testable. A key goal for the testing committee is to find and report the identification of bugs and the identification of issues about the ability of the standard to meet the objectives.

. Once a bug is found, the testing committees’ job is to accurately communicate its impact and describe any workaround solutions that could lessen its impact as well as provide feedback back to the development team.

The Testing Team consists of the following members:

| Name | Role |
| --- | --- |
| Dirk Beth | Testing Facilitator |
| Bob Birmingham | Tester |
| Scott Becker |  |
| Anne Mieke |  |
| Leah Kleylein |  |
| George Waidell |  |
| Corey Oravetz |  |
| Diane Sheffer |  |
| Joseph Mumma |  |
| Claire Holmes |  |
| FDA |  |

The membership is open to the public.

# Project Risks

All issues identified that may impact the successful outcome of this project must be submitted immediately to the Project Leader. All issues will be formally documented and logged in a project issue log that will be managed throughout the project lifecycle.  The Project Leader will review these to determine the potential project impacts and whether the issue will be escalated for resolution.  As issues are identified, they will be assigned to the appropriate individual or group for resolution in the requested specified timeframe.

As issues are resolved, they will be closed. Before the project can be formally closed, all open issues must be addressed and resolved.   This will be maintained through an issue tracking log.

Listed below are the project risks identified to at the time of the project plan completion.  For further details please refer to the log on the HL7 wiki. www.hl7.org

- Testing and tools - environment

- Testing  resources, timing

- Device industry resources to provide thorough input within the project timeline

- BRIDG harmonisation schedule

- Scope expansion beyond resource & expertise level

- PDUFA IV timeline requirements

- International engagement

- Diversity of requirements

# Communications

Communications are defined as meetings/material meant to share or convey information that is not specifically a deliverable of the project (e.g., storyboards, RMIM, test plan. These deliverables will be shared and published using established communications mechanisms.

Communications mechanisms include:

HL7 Wiki

HL7 RPS Listserv

Scheduled Project teleconferences

In addition to the above, subgroups may establish teleconferences and shared working areas at their discretion.

The table below describes the core communications activities expected during the project:

| Communication | Responsible Party | Frequency | Purpose | Location/Destination |
| --- | --- | --- | --- | --- |
| Scheduled RPS project teleconference | Project Facilitator | Bi-weekly or as required | Review project status & activities | Minutes, action items, decisions and project updates will be posted on HL7 wiki within 5 business days |
| Advisory Committee meetings | Chair & Co Chair | Monthly or as required | Agenda based on project phase & status, see Advisory Committee description | Minutes will be posted on HL7 wiki within 5 business days |
| Risk Log | Project Facilitator | Monthly or as updated | Track and manage project risks and mitigations | Wiki |
| Subgroup meetings, teleconferences | Subgroup Team Lead | As scheduled | Working meetings | Minutes, action items, decisions and project updates will be posted on HL7 wiki within 5 business days |
| Outreach activities | Advisory Committee Members | As required and scheduled | Stakeholder outreach, education, awareness | Materials published on Wiki prior to outreach activity |
| Document peer reviews | Advisory Committee Members | As required | Peer review of project deliverables for engagement of and value to stakeholder | Aggregate comments posted on Listserv |

# Project Milestones

LIFECYCLE ONE		07/24/08 to 01/15/10

Iteration 1			08/24/08 to 05/25/09

- Requirements		08/26/08 to 10/13/08

- Development		10/14/08 to 01/12/09

- Testing Planning		10/14/08 to 01/12/09

- Testing Execution	01/13/09 to 05/25/09

Iteration 2			10/21/08 to 08/24/09

- Requirements		10/21/08 to 01/13/09

- Development		01/14/09 to 03/09/09

- Testing			05/26/09 to 08/24/09 (starts when iteration 1 testing ends)

Iteration 3  			08/25/09 to 01/15/10

- Revisit iteration 1&2	08/25/09 to 10/05/09

- Ballot Discussion		10/06/09 to 11/02/09

- DSTU Ballot Prep	11/03/09 to 11/27/09

- DSTU Ballot		11/30/09 to 12/28/08

- Ballot Reconciliation	12/29/09 to 01/15/10

LIFECYCLE TWO 		01/18/10 to TBD       (based on input and feedback from lifecycle one)

# Workgroup Engagement

Project Plan

This Project Plan identifies the project’s deliverables, timing, and scope.  It also includes specific reference to the project’s governance.

RCRIM RPS2 Workgroup Commitments

We need your commitment and continued support to champion this initiative throughout the HL7 process. Specifically, to:

- Stay the course of the current scope outlined in the HL7 project scoping document for RPS R2, and to adhere to the appropriate change control processes established if there is a need to change the scope.

- Work within the established project governance roles and processes as defined by HL7.

- Aid in the development of the business requirements

- Aid in the testing of the standard

- Aid in the implementation

- Aid in the positive communication and acceptance of the standard

- Aid in issue resolution and support the agreed upon solutions

- Provide access to required information and resources that may be outside the formal assignment to the initiative.

- Resource planning (people and funding) to support project schedule

- Review and comment on the project objectives and performance indicators for measurement of project success

- Establishment of appropriate accountability for creating and signing project acceptance documents

# Project Controls

### Project schedule (high level work plan)

A project schedule identifying the prime, start and finish and durations of project deliverables will be developed and managed throughout the life of the project.  This plan will be available to all project team members. The plan will include any assumptions used to estimate the project effort and approach.

### Project status reporting

Project status will be provided; the regularity of the reporting will be determined by the requirements of Responsible Party and the project type. Refer to the Communications section of this document.

### Project Change Management

All change requests will formally documented and managed through the Change Management processes and approvals.

As change requests are submitted, they will be assigned for assessment and impacts, after which it will be determined if the change request is approved or not. Changes to the scope, schedule, resources, and risk of the project caused by an approved change request will be documented, logged and communicated to the advisory committee and to the project team at large. Rejected change requests will be returned to the originator with the rationale for rejecting the change request.

All artifacts will be agreed upon using the Peer Review Process.

The artifacts created by any activity are used in the development of artifacts at subsequent steps in the process. Earlier artifacts are analyzed and refined or expanded upon during later activities. 
While the activities are in sequence, the process of Requirements Documentation is iterative and is not a manifestation of the Waterfall approach to “gather all the requirements before proceeding to design or implementation.” As one moves from activity to activity during the Requirements Documentation process there will be situations that require revising or expanding previous artifacts. 
Even after this process has delivered the Requirements Specification to the next step in the process, it will usually be necessary to revisit the requirements when issues are discovered during subsequent Healthcare Development Framework (HDF) processes. There may be missing requirements, ambiguities, inconsistencies, etc. While it is important that requirements be generally stable before model development begins, it is also important to leave open the ability to modify the Requirements Specification as issues are discovered. It is useful to document these changes so that those reviewing ballot materials can review the history and understand how the model meets the requirements.  At some point requirements are locked and new requirements will be captured and tested in subsequent versions of the standard.

Please see CM Log tab in the Issues/Risks/CM Tracking Log on the HL7 wiki. www.hl7.org

### Project Issue Management

All issues identified that may impact the successful outcome of this project must be submitted immediately to the Project Leader. All issues will be formally documented and logged in a project issue log that will be managed throughout the project lifecycle.  The Project Leader will review these to determine the potential project impacts and whether the issue will be escalated for resolution.  As issues are identified, they will be assigned to the appropriate individual or group for resolution in the requested specified timeframe.

As issues are resolved, they will be closed. Before the project can be formally closed, all open issues must be addressed and resolved.   This will be maintained through an issue tracking log.