**HL7 Patient Care Work Group**

**Allergy/Intolerance/Adverse Reaction Topic Sub-Group Meeting Minutes**

**Date: May 22, 2013**

Co-Chairs: Stephen Chu, Elaine Ayres Scribe: Elaine Ayres

|  |  |
| --- | --- |
| **Name** | **Present on 5/22/13** |
| Elaine Ayres | X |
| Stephen Chu | X |
| Jean Duteau |  |
| Russell Leftwich |  |
| Rob Hausam |  |
| Kevin Coonan | X |

**Agenda for Wednesday, May 22, 2013 at 5 PM EDT**

1. Review agenda for today
2. Discuss and approve amended Project Scope Statement for Allergy and Intolerance Clinical Models based on questions from Pharmacy and OO (attached)
3. PSS is missing a 2nd implementer that is mandatory for DSTU
4. The V3 artifacts listed is not complete - need interactions, etc.
5. It is not clear what this will be says DSTU to Normative, but section 3d does not include steps to take this to normative
6. Include template but it is not clear how this ties into CDA R2. How will you use the templates that are mentioned?
7. V3 web services Please provide clarification on what this
8. Status of DAM ballot reconciliation
9. Determine schedule for completion of changes to DAM and publication.
10. FHIR any outstanding issues?
11. Agenda for June 5 call.

**Minutes** –

Have outstanding minutes from April 24th call – Elaine will complete and circulate.

**PSS Statement Review**

****

The three Patient Care WG co-chairs on the call reviewed the draft PSS for the next phase of allergy and intolerance work. The updated project scope statement now addresses the questions raised by the Pharmacy WG. Elaine will review the updated PSS with Pharmacy on their May 27th call. Elaine will also send the amended scope statement back to DSS and OO for their concurrence.

Several key decisions were made re project #1004

1. The project will now be DSTU to normative including ANSI related submissions and approvals.
2. Follow-on projects will be planned to develop template(s), an implementation guide and SOA services.

Ballot schedule for September:

July 7 – NIB due

July 14 – Initial content due

July 21 – Preview and CMET content due

July 28 – Ballot reconciliation must be complete for last cycle (this is complete !!)

August 4 – Final content

August 12 – Ballot opens

**FHIR**

Lloyd McKenzie has additional questions about FHIR resources for allergy and intolerance. Stephen will confer with Lloyd regarding availability for a call. The June 5th call was suggested.

**Agenda for Wednesday, June 5, 2013 WG call**

1. Review and adjust agenda for June 5, 2013.
2. Provide update on Project Scope Statement approvals (Pharmacy, OO, DSS, DESD and TSC)
3. Assist Jean and Lorraine with information required for developing the RMIM and CMET elements.
4. FHIR resources – Lloyd McKenzie?
5. Agenda for June 19, 2013