- Project Name, ID and Products

| Decision Making Practices Template & Default Maintenance | Project ID: |
| --- | --- |
| Non Product Project- (Educ. Marketing, Elec. Services, etc.) | V3 Documents - Knowledge |
| Arden Syntax | V3 Foundation – RIM |
| Clinical Context Object Workgroup (CCOW) | V3 Foundation – Vocab Domains & Value Sets |
| Domain Analysis Model (DAM) | V3 Messages - Administrative |
| Electronic Health Record (EHR) | V3 Messages - Clinical |
| V2 Messages – Administrative | V3 Messages - Departmental |
| V2 Messages - Clinical | V3 Messages - Infrastructure |
| V2 Messages - Departmental | V3 Rules - GELLO |
| V2 Messages – Infrastructure | V3 Services – Java Services (ITS Work Group) |
| V3 Documents – Administrative (e.g. SPL) | V3 Services – Web Services |
| V3 Documents – Clinical (e.g. CDA) | - New Product Definition - |

- Project Intent

| Create new standard Revise current standard Supplement to a current standard Implementation Guide will be created/modified | Reaffirmation of a standard Withdraw current standard N/A (Project not directly related to an HL7 Standard) |
| --- | --- |

  - Ballot Type

| Comment Only Informative DSTU | Normative Joint Ballot (with other SDOs or HL7 Work Groups) N/A (project won’t go through ballot) |
| --- | --- |
| Add any additional ballot information here. If artifacts will be jointly balloted with other HL7 Work Groups or other SDOs, list the other groups. |

  - Public Document

Public Document(s) to be created?

- Sponsoring Group(s) / Project Team

| Primary Sponsor/Work Group (1 Mandatory) | PIC |
| --- | --- |
| Co-sponsor Work Group(s) | None |
| Project Team: |  |
| Project facilitator (1 Mandatory) | Helen Stevens |
| Other interested parties | HL7 Staff |
| Multi-disciplinary project team (recommended) | N/A |
| Modeling facilitator | N/A |
| Publishing facilitator | N/A |
| Vocabulary facilitator | N/A |
| Domain expert rep | N/A |
| Data Analyst facilitator | N/A |
| Business requirement analyst |  |
| Requirements process facilitator |  |
| Implementers (2 Mandatory for DSTU projects): |
| 1) |
| 2) |

- Project Definition

  - Project Scope

This project is for the bi-annual maintenance of the HL7 Decision Making Practices (DMP) Template and the WG Default DMP. It will update the DMP template based on input received from members and co-chairs and to reflect updated processes at HL7. Based on the new DMP template a default that will apply to all Work Groups who do not approve their own DMPs will be created.

  - Project Need

There have been numerous suggestions for improvements and updates to the DMP since it was last published. HL7 processes have changed and the expectations and needs of the workgroups have also evolved. The current DMP is out of date and missing key information and processes that have been independently created in individual WG DMPs.

  - Success Criteria

The following will help define if this project has completed the efforts intended: New DMP Template and Default published and distributed to co-chairs reflecting all input received.

  - Project Objectives / Deliverables / Target Dates

|  | Target Date |
| --- | --- |
| Solicitation of additional changes/enhancements from co-chairs, review of existing DMP variants approved by workgroups. | May 2010 WGM |
| Initial re-draft of DMP based on received input and process changes and review by PIC members | June 2010 |
| Updated DMP distributed for endorsement by TSC | August 2010 |
| Education sessions and distribution to co-chairs | October 2010 WGM |
| Close project and update all material | January 2011 WGM |

  - Project Dependencies

Bandwidth of participants

  - Project Document Repository Location

All documents should be stored on PIC page on HL7.org and PIC wiki at wiki.hl7.org.

  - Backwards Compatibility

Are the items being produced by this project backward compatible? Yes No Don’t Know N/A

- Project Approval Dates

| Sponsoring Group Approval Date | Work Group Approval Date |
| --- | --- |
| Steering Division Approval Date | SD Approval Date |
| Technical Steering Committee Approval Date | TSC Approval Date |

- External Project Collaboration

N/A

  - Stakeholders / Vendors / Providers

| Stakeholders | Vendors | Providers |
| --- | --- | --- |
| Clinical and Public Health Laboratories | Pharmaceutical | Clinical and Public Health Laboratories |
| Immunization Registries | EHR, PHR | Emergency Services |
| Quality Reporting Agencies | Equipment | Local and State Departments of Health |
| Regulatory Agency | Health Care IT | Medical Imaging Service |
| Standards Development Organizations (SDOs) | Clinical Decision Support Systems | Healthcare Institutions (hospitals, long term care, home care, mental health) |
| Payors | Lab | Other (specify in text box below) |
| Other (specify in text box below) | HIS | N/A |
| N/A | Other (specify below) |  |
|  | N/A |  |
| Other: HL7 Staff and co-chairs |

- Realm

| Universal | Realm Specific (Enter “U.S.” or name of HL7 affiliate here) |
| --- | --- |

- Roadmap Reference

http://www.hl7.org/documentcomments/index.cfm

Check which Roadmap Strategy best relates to your project. Lead the development of global technical and functional health informatics standards. Streamline the HL7 standards development process. Facilitate HL7 standards adoption and implementation. Define an overarching and internally consistent interoperability framework. Ensure broad and encompassing stakeholder engagement in the standards development process. Align HL7's business and revenue models to be responsive to national bodies while supporting global standards development. None of the above apply to this project.