**ENCPRS R2 Project**

**Task List & Schedule**

Last Updated: February 22, 2018

Task date ranges start on Friday, and end with our weekly project meetings on Thursdays

|  |  |  |  |
| --- | --- | --- | --- |
| Date Range | Task Description | Who | Status |
| 2/16-2/22 | Review Direct Care EHRS-FM R1 | SMEs | In Progress |
| 2/16-2/22 | Create first two sections of ENCPRS R2 in the profiling tool | Patrick | In Progress |
| 2/23-3/1 | Review Overarching Criteria and Care Provision sections EHRS-FM R2 | SMEs | Next steps |
| 2/23-3/1 | Review EHRS-FM R1 sections* Supportive Functions
* Information Infrastructure
 | SMEs | Next steps |
| 2/23-3/1 | Compile and publish first two sections of ENCPRS R2 using the tooling* Overarching Criteria
* Care Provision
 | Patrick | Next steps |
| 3/2-3/8 | Review and comment first two sections of ENCPRS R2 | SMEs | Not started |
| 3/9-3/15 | Review and comment first two sections of ENCPRS R2 | SMEs | Not started |
| 3/16-3/22 | Review and comment first two sections of ENCPRS R2 | SMEs | Not started |
| 3/23-3/29 | Review and comment first two sections of ENCPRS R2 | SMEs | Not started |
| 3/30-4/5 | Compile and publish next two sections of ENCPRS R2* Care Provision Support
* Record Infrastructure
 | Patrick | Not started |
| 4/12, 4/19, 4/26 | April Meetings – Review and comment sections Care Provision Support, Record Infrastructure | SMEs | Not started |
| 4/26-5/3 | Compile and publish last section of ENCPRS R2* Trust Infrastructure
 | Patrick | Not started |
| 5/10, 5/17, 5/24, 5/31 | May Meetings incl. WGM in Cologne – Review Trust Infrastructure; provide overview and update to EHR | SMEs | Not started |
| 6/1-6/7 | Fix whatever | Patrick | Not started |
| 6/7, 6/14, 6/21, 6/28 | Finalize ENCPRS R2 | SMEs | Not started |
| 6/29-7/12 | Produce ballot materials | Patrick | Not started |
| 8/19 | Ballot submission content deadline | Patrick | Not started |
| 9/25-10/5 | September Meetings – support ballot reconciliation | All | Not started |

Sections for ENCPRS R2 based on EHRS-FM R2

* Overarching Criteria
* Care Provision
* Care Provision Support
* Record Infrastructure
* Trust Infrastructure