|  | Project Deliverable | Tasks/Action Items | Target Deadlines |
| --- | --- | --- | --- |
| 1a | Review existing diabetes data sets from USF/research protocols, the Netherlands, Canada, and quality measurement. Select a sample set of common T1D assessment data elements to be used in this prototype project. | Wendy incorporating Canadian elements into the master data element spreadsheet (week of February 1st) Rachel transferring elements from the original spreadsheet to master element spreadsheet and further refining elements as part of the process (week of February 8th). Crystal adding quality measurement and atomic data elements known to date to master data element spreadsheet (week of February 15th). NOTE: additional atomic elements will be incorporated as mapping and modeling efforts are conducted. Rachel/Crystal/Wendy to conduct review of master element spreadsheet to make final edits/modifications (week of February 22nd). Team members conduct final review and approval of the sample set of common T1D assessment data elements for use in this project (February 26th). | Target date: February 26, 2010 |
| 1b | Model a small set of data elements, identified in #1a above, to create a visual depiction of some data elements, exhibit relationship to DCMs, and demonstrate how patterns can be identified in support of future large scale harmonization efforts. | Donna/Luigi modeling a few data element samples with input from Crystal, Rachel and Wendy (February/March 2010). Donna/Luigi to review draft modeled data elements with the team to demonstrate concepts and discuss (March 19th). Donna/Luigi/Crystal/Rachel/Wendy to incorporate input from the team, and document conclusions/recommendations (March 19, 2010). | Target date: April 2, 2010 |
| 1c | Map the same small set of data elements, identified in #1b above, to atomic data elements that are available (or could be available) in EHRs. | Crystal (and/or other interested team members) mapping the same small set of data elements, identified in #1b above, to atomic data elements that are available (or could be available) in EHRs. Atomic elements from this task will also feed into the modeling process (#1b) above. Atomic elements identified as part of the mapping and modeling processes will also be maintained in the master element spreadsheet (February 2010). Crystal to share atomic element mapping results with team in conjunction with modeling review noted above (March 5th). | Target date: March 5, 2010 |
| 2 | Map the atomic data elements, identified as part of the mapping effort under#1c above, to specific functions in the EHR-S FM. Mapping to the Child Health and Clinical Research Functional Profiles will only be accomplished if domain expert volunteers are available to conduct this piece of work. | _______ to develop a sample format to map atomic data element to EHR-S FM conformance statements for team review/input (February 26, 2010) _______ to map atomic data elements to EHR-S FM conformance statements (March 2010) _______ to review draft atomic element/EHR-S FM mapping with the team and discuss (March 26, 2010) _______ to incorporate input from the team and document conclusions/recommendations (April 9, 2010) | Target date: April 9, 2010 |
| 3 | In parallel to #2 above, map the atomic data elements and corresponding EHR-S FM conformance statements to the Interoperability and Lifecycle Models with the EHR-S FM and Child Health and Clinical Research Functional Profiles. | Pat V./Gary to draft use case to support Interoperability/Lifecycle Model mapping (TBD) Gary to develop a sample format depicting how the data element models (groupings of data elements) can be captured in templates as part of a clinical workflow (March 26, 2010). Gary (and other interested/required team members) to conduct Interoperability/Lifecycle Model mapping (March/April 2010) Gary to review draft mapping with the team and discuss (April 16, 2010). Gary to incorporate input from the team and document conclusions/recommendations (April 30, 2010) | Target date: April 30, 2010 |
| 4 | Document the process, methodology, conclusions and recommendations. | Crystal/Rachel to document process/methodology for team review/input (April 9, 2010). Crystal to compile conclusions/recommendation from each project stage (ongoing). Crystal to collate/package final set of artifacts for team review/input (May 7, 2010). | Target date: May 2010 |
| 5 | Finalize and disseminate project results. | Present final project package to EHR WG (TBD) | Target date: May 2010 |
| n/a | Discuss work in progress at the Bridging the Chasm (CIIC) meeting, if the opportunity arises. | No further action at this time. Further action will be taken if/when the CIIC convenes. Rachel presenting an overview of the project methodology during the AMIA Clinical Research Summit (March 13th) | n/a |
| n/a | Develop a DCM or use an existing series of DCMs (from The Netherlands) and tie them to the DAMs and the EHR-S FM and Child Health and Clinical Research Functional Profiles. | This task may be replaced with task #1b above. | n/a |

Diabe-DS Meeting Schedule

Dial in: 770-657-9270 / Pass code: 510269#

February 5, 2010, 12:00-1:00 ET

- Review work plan (Crystal)

- Review Canada data element additions (Wendy)

February 12, 2010, 12:00-1:00 ET

- Review new research elements added to the spreadsheet (Rachel)

February 19, 2010, 12:00-1:00 ET

- Review new quality measurement and atomic data elements added to the spreadsheet (Crystal)

February 26, 2010, 12:00-1:00 ET

- Project team to review and approve final sample set of common T1D assessment data elements for use in this project (master data element spreadsheet) (Crystal/Rachel/Wendy)

- Review sample format to map atomic data element to EHR-S FM conformance statements for team review/input (TBD)

March 5, 2010, 12:00-1:00 ET

- Week of HIMSS – verify availability for a call

- Share atomic element mapping results with team (Crystal)

March 12, 2010, 12:00-1:00 ET

- Rachel/Don unavailable

- Rachel presenting an overview of this work during the AMIA Clinical Research Summit (March 13th)

- Check availability of team due to potential spring break schedules

March 19, 2010, 12:00-1:00 ET

- Don unavailable

- Donna/Luigi to review draft modeled data elements with the team to demonstrate concepts and discuss next steps

- Verify availability of team due to potential spring break schedules

March 26, 2010, 12:00-1:00 ET

- Review draft atomic element/EHR-S FM mapping with the team and discuss (TBD)

- Present sample format depicting how the data element models (groupings of data elements) can be captured in templates as part of a clinical workflow (Gary)

April 2, 2010, 12:00-1:00 ET

- Verify availability of team due to Good Friday holiday

- Review conclusions/recommendations related to the modeling component (Donna/Luigi/Crystal/Rachel/Wendy)

April 9, 2010, 12:00-1:00 ET

- Present draft process/methodology documentation for team review/input (Crystal/Rachel)

- Present conclusions/recommendations related to mapping atomic data element to EHR-S FM conformance statements (TBD)

April 16, 2010, 12:00-1:00 ET

- Review draft Interoperability/Lifecycle Model mapping (Gary)

April 23, 2010, 12:00-1:00 ET

April 30, 2010, 12:00-1:00 ET

- Present conclusions/recommendations depicting how the data element models (groupings of data elements) can be captured in templates as part of a clinical workflow (Gary)

May 7, 2010, 12:00-1:00 ET

- Present final set of artifacts for team review/input (Crystal)

May 14, 2010, 12:00-1:00 ET

May 16 – 21, 2010

- HL7 Working Group Meeting, Rio de Janeiro, Brazil

- Assess team member availability to present a project update to the EHR WG or schedule time to present information during an EHR WG conference call