Minutes RCRIM Terminology Call

Date: Thursday May 13, 2010

16 Participants: Laura Allen (Merck), Melissa Cook (Independent), Laura DiTullio (Independent), Kristi Eckerson (Emory), Margaret Haber (NCI), Amy Jacobs (Imco), Mary Lenzen (Octagon), Debbie O’Neil (Merck), Erin Muhlbradt (NCI EVS), Sophia Paterakis (Amgen),Terry Quinn (NCI EVS), Frank Senk (Astra Zeneca), Chris Tolk (CDISC), CoCo Tsai (FDA), Mike Woodcock (Mayo), Julia Zhang (Genzyme)

Regrets: Randall Austin (GSK), Bron Kisler (CDISC), Liz Nulton-Bodiford (GSK), Jennifer Fostel (NIH), Peggy Zorn (Thompson Reuters)

Topic: CDISC/RCRIM terminology development and harmonization

- Approval of Minutes from April 22

The minutes were approved with one correction. Reminder: all final minutes are published on the HL7 wiki. http://wiki.hl7.org/index.php?title=RCRIM_Vocabulary

- Package 5 Terminology Teams

General Team - Almost complete with the review of terms

Micro - NIC EVS has definitions that the team will review by email

ADaM - Complete

PK - Reviewing the new list, about 2/3 final.

Lab - Working through about 100 new terms, about 2/3 final.

The goal is for each group to have the terms ready for public review the end of May 2010. This 	may be delayed to the middle of June.

- Update on FDA Vocabulary Projects

- Substance Registration System (SRS) - entering food and cheese. There is no public access currently but there will be a public interface soon. All of the terms will be in NCIt.

- Pill box project, imaging of tablets and capsules for Structured Product Labeling (SPL), is progressing. There may be some terminology alignment with for example color.

- Update on other RCRIM Projects

No update.

- External Harmonization

No update.

- New Term Request Mechanism

We received 46 requests for 2010 Q1; Three Type 1, 6 Type II and 37 Type III. Most of the Type III requests were for new lab terms that have been added to package 5.

So far in Q2 we have received one Type II request and 4 Type III requests.

- Update on CDISC Terminology Projects

- SEND: Public review is being planned for June 2010.

- Governance/Implementation Team: Starting to review the IG. Public review will most likely take place in late summer.

- Glossary: No new update

- Oncology: Terminology will be needed for some variables. Chris will monitor with the team.

- Devices: The device group’s document is in a very early stage. Chris is monitoring to see when terminology is needed.

- Other Development Activities

- Polycystic Kidney Disease: The team is working on developing standard definitions for the data element. NCI provided their standard definitions and the team is either accepting these definitions or developing their own.

- Alzheimer’s Disease and Parkinson’s Disease: we are working with C-Path in the development work. For Parkinson’s disease we are also working with NINDS to monitor their work on data definitions.

- AOB

None.

Next TC:

- Thursday, May 27, 2010

- Thursday, June 10, 2010 (may be cancelled)

- Thursday, June 24, 2010

Drafted: C. Tolk/May 13, 2010

Approved: June 24, 2010