| HL7 PROJECT Project Time Line (Revised 6/29/07) |
| --- |
| Task | Days | Start | End | Responsibility | Comments |
| HL7 (30 min. course) | 154d | Wed 1/31/07 | Mon 9/3/07 |  |  |
| Planning | 80d |  | Done |  |  |
| Write Project Work Plan | 1d |  | Done | Dennis |  |
| Review/Revise Work Plan | 1d |  | Done | HL7 |  |
| Write/Collect Content | 78d |  | Done | Sonia & HL7 |  |
| Analysis | 10d |  | Done |  |  |
| Analyze Presentation & Content Analysis | 10d |  | Done | Sonia |  |
| Design | 10d |  | Done |  |  |
| Write Content Outline/Map & Scope/Sequence | 2d |  | Done | Sonia |  |
| "Determine Overall Look - Identify Graphics, Photos, etc. Needs" | 1d |  | Done | Walt |  |
| Layout Course Treatment-Essence of what you see and hear | 3d |  | Done | Sonia |  |
| Review Course Treatment | 7d |  | Done | HL7 Team |  |
| Revise Course Treatment | 1d |  | Done | Sonia |  |
| Signoff On Course Treatment | 0d |  | Done | HL7 |  |
| Development | 17d | Tue 6/26/07 | Wed 7/18/07 |  |  |
| Develop/Write Script/Storyboard | 10d | Tue 6/26/07 | Mon 7/9/07 | Sonia | In process |
| Develop Graphic Renditions | 7d | Tue 7/10/07 | Wed 7/18/07 | Walt |  |
| "Take, Supply, and Find Photos" | 7d | Tue 7/10/07 | Wed 7/18/07 | HL7 & Walt |  |
| Internal QA of Script/Storyboard | 1d | Tue 7/10/07 | Tue 7/10/07 | Beth |  |
| Revise Script/Storyboard | 1d | Wed 7/11/07 | Wed 7/11/07 | Sonia |  |
| External QA Script/Storyboard | 3d | Thu 7/12/07 | Mon 7/16/07 | HL7 |  |
| Revise Script/ Storyboard | 2d | Tue 7/17/07 | Wed 7/18/07 | Sonia |  |
| Signoff On Script/Storyboard | 0d | Wed 7/18/07 | Wed 7/18/07 | HL7 |  |
| Production | 15d | Thu 7/19/07 | Wed 8/8/07 |  |  |
| "Produce Graphics-photos, Illustrations, Flash, Watermarks, etc." | 10d | Thu 7/19/07 | Wed 8/1/07 | Walt |  |
| Produce Audio | 5d | Thu 7/19/07 | Wed 7/25/07 | Dave M |  |
| Integrate Course Assets | 5d | Thu 8/2/07 | Wed 8/8/07 | Sonia |  |
| Quality Assurance | 19d | Thu 8/9/07 | Tue 9/4/07 |  |  |
| Conduct Acceptance System Testing | 2d | Thu 8/9/07 | Fri 8/10/07 | Beth |  |
| Fix Bugs | 3d | Mon 8/13/07 | Wed 8/15/07 | LS Team |  |
| Conduct Alpha Test | 3d | Thu 8/16/07 | Mon 8/20/07 | HL7 |  |
| Fix Bugs | 5d | Tue 8/21/07 | Mon 8/27/07 | LS Team |  |
| Conduct Beta Test | 3d | Tue 8/28/07 | Thu 8/30/07 | HL7 |  |
| Fix Bugs | 3d | Fri 8/31/07 | Tue 9/4/07 | LS Team |  |
| Launch | 3d | Wed 9/5/07 | Fri 9/7/07 |  |  |
| Signoff On Approved Course to Launch | 1d | Wed 9/5/07 | Wed 9/5/07 | HL7 |  |
| Burn 10 CD-ROMS | 2d | Thu 9/6/07 | Fri 9/7/07 | Sonia |  |
| Launch | 0d | Fri 9/7/07 | Fri 9/7/07 | Sonia |  |