Project Approval Process For Work Group Sponsored Projects Version 2010 Release 1.0

Project Services Work Group

David Hamill, pmo@hl7.org

Publication Date: October 7, 2010

Table of Contents									    Page

Overview: The HL7 Project Approval Process for Work Group Sponsored Projects	4

Step 1:  Create a Project Scope Statement (PSS)	4

Step 2:  Sponsoring and Co-Sponsoring Work Group(s) review and approve the Project Scope Statement	4

Step 3:  Submit Project Scope Statement to “leader” groups for review/approval	4

Step 4:  PMO enters the Project Scope Statement into Project Insight	4

Step 5:  “Leader” Group reviews/approves the Project Scope Statement	4

Step 6:  Submit Project Scope Statement to TSC for review and / or approval	4

Step 7:  The HL7 PMO and Project Services Committee insure that HL7 project methodology is adhered to	4

What approvals do I need to obtain?	5

How to use this document …	6

Shall / Should / May Definitions	7

Project Sponsor: TSC Work Group (including ArB).  Most projects fall into this area.	8

FAQ – Frequently Asked Questions	16

How do I search/view HL7 Projects?	16

Where can I find the Project Scope Statement Template?	16

Who is the project facilitator?	16

How do I know the approval status of my project?	16

Where can I find the list of Steering Division Leaders or Steering Division Project Facilitators?	16

I’ve submitted my PSS to my Steering Division for approval but haven’t heard anything from them.  What should I do?	17

The scope or objective of my project changed.  Do I need to create a new PSS?	17

What approvals are needed if I revise my existing PSS, say the project’s scope changes?	17

What ballot types are required to go through the project approval process?	17

When withdrawing or reaffirming a standard, does a PSS need to be created and go through the review/approval process?	18

Do I need to go through the project approval process if a standard has expired and will not be reaffirmed?	18

Do I need to update the PSS if I discover after it’s approved that I need to coordinate ballots with other HL7 Work Groups?	18

What is the approval process for HL7 projects that collaborate with ISO or the JIC?	18

How should a Work Group document the voting results after seeking approval for the PSS?	18

# Overview: The HL7 Project Approval Process for Work Group Sponsored Projects

In summary, the HL7 project approval process is as follows:

## Step 1:  Create a Project Scope Statement (PSS)

## Step 2:  Sponsoring and Co-Sponsoring Work Group(s) review and approve the Project Scope Statement

## Step 3:  Submit Project Scope Statement to “leader” groups for review/approval

## Step 4:  PMO enters the Project Scope Statement into Project Insight

## Step 5:  “Leader” Group reviews/approves the Project Scope Statement

## Step 6:  Submit Project Scope Statement to TSC for review and / or approval

## Step 7:  The HL7 PMO and Project Services Committee insure that HL7 project methodology is adhered to

# What approvals do I need to obtain?

The table below summarizes the approvals needed based on the group sponsoring the project.

| If the Project’s Sponsor is a… | Approvals shall be gathered from the following committees… | The following committees will be informed of the project… |
| --- | --- | --- |
| TSC Work Group (most projects fall into this area) | - Work Group - Steering Division(s) - TSC | - International Affiliates - Co-Chairs |
| ArB | - Work Group - TSC | - International Affiliates - Co-Chairs |

PSS approvals are typically done via conference calls.  However, if desired, the approval can be through email or a poll (say, a Doodle Poll via www.doodle.com), if the Work Group, Committee, or Council has defined an e-Vote process in their Decision Making Practices.  When doing this, include the URL to the Doodle poll and indicate a deadline date for the review and approval within the email requesting review/approval.

# How to use this document …

Follow the steps based on your project’s sponsor.  The color coding is used throughout the document for easier reading.

| If the Project’s Sponsor is a… | Within this document, go to the following hyperlinked section … |
| --- | --- |
| TSC Work Group (most projects fall into this area) Includes ArB. | Project Sponsor: TSC Work Group (including ArB). Most projects fall into this area. |

# Shall / Should / May Definitions

This describes the terminology for expressing the stringency of a conformance statement.   HL7 adheres to ISO/IEC directive, Appendix G, as delineated in the following table:

Table 1: Stringent Use of SHALL, SHOULD and Other Modal Verbs To Convey the Sense of:  Use the Following:

Required/Mandatory SHALL SHALL NOT

Best Practice/Recommendation SHOULD SHOULD NOT

Acceptable/Permitted MAY NEED NOT

Examples:

You SHALL clean your room before going out.

The action is REQUIRED. If the specified action is not performed, the following action is NOT allowed.

You SHOULD clean your room before going out.

The action is RECOMMENDED or a BEST PRACTICE. This is a practice that is believed to be beneficial.

You MAY clean your room before going out.

This action is ALLOWED.

# Project Sponsor: TSC Work Group (including ArB).  Most projects fall into this area.

Step 1:  Create a Project Scope Statement (PSS).

| If the Project’s Sponsor is a… | Actions | Deliverables |
| --- | --- | --- |
| TSC Work Group (most projects fall into this area) Includes ArB. | The Project Facilitator shall work with members of their Work Group to complete a Project Scope Statement (PSS) using the most recent version of the PSS Template (MS Word document) located at www.HL7.org > Participate > Templates (http://www.hl7.org/participate/templates.cfm). The same work shall be followed whether it’s a new project, reaffirming a standard, or a scope change to an existing project. | PSS completed and ready to be reviewed by the sponsoring and co-sponsoring Work Group(s). |
| ArB | Same as above. | Same as above. |

Step 2:  Sponsoring Work Group(s) reviews and approves the Project Scope Statement.

Reviews should focus on the following within the PSS:

- is this PSS clear in terms of its scope and deliverable(s)

- is it within the scope of the sponsoring committee

- how is it related to other projects

- how is it related to the activities of other committees

PSS approvals are typically done via conference calls.  However, if desired, the approval can be through email or a poll (say, a Doodle Poll via www.doodle.com), if the Work Group, Committee, or Council has defined an e-Vote process in their Decision Making Practices.  When doing this, include the URL to the Doodle poll and indicate a deadline date for the review and approval within the email requesting review/approval.

| If the Project’s Sponsor is a… | Actions | Deliverables |
| --- | --- | --- |
| TSC Work Group (most projects fall into this area) Includes ArB. | The Project Facilitator shall submit the completed PSS to the sponsoring and co-sponsoring Work Group(s). The sponsoring and co-sponsoring Work Group(s) shall review and approve the PSS. Reviewers should direct any questions / comments to the Project Facilitator. Reaffirming a standard or a scope change to an adjusted Project Scope Statement shall all go through the same approval process, timelines and deadlines as new projects. | PSS reviewed and approved by the sponsoring and co-sponsoring Work Group(s). |
| ArB | Same as above. | Same as above. |

Step 3:  Submit Project Scope Statement to “leader” groups for review/approval.

PSS approvals are typically done via conference calls.  However, if desired, the approval can be through email or a poll (say, a Doodle Poll via www.doodle.com), if the Work Group, Committee, or Council has defined an e-Vote process in their Decision Making Practices.  When doing this, include the URL to the Doodle poll and indicate a deadline date for the review and approval within the email requesting review/approval.

| If the Project’s Sponsor is a… | Actions | Deliverables |
| --- | --- | --- |
| TSC Work Group (most projects fall into this area) ArB – see below. | Project Facilitator shall email the WG-approved PSS to: - Sponsoring Work Group’s Steering Division listserv. If Project Facilitator is not subscribed to the listserv, email the SD Leaders (located via their SD page at http://www.hl7.org/Special/committees/index.cfm) and SD Project Facilitator (listed via a PDF on http://www.hl7.org/About/hl7facilitators.cfm). - HL7 Project Management Office (pmo@hl7.org) - Other Steering Division leaders and their SD Project Facilitator) if the co-sponsoring WG is in a different SD. NOTE: For a project that will be BALLOTED, typically, this submission corresponds to the 2nd Sunday after the WGM deadline labeled as ‘New Project Scope Deadline’ on the publishing calendar (located at http://www.hl7.org/Special/committees/publishing/schedules.cfm). From this deadline, there is about a 6 week timeframe to gather the SD and TSC approvals so that the PSS has all it’s approvals in time to submit the project in the upcoming ballot cycle. ArB projects – see below. | WG-approved PSS emailed to sponsoring and co-sponsoring Work Group’s Steering Division(s) and PMO. |
| ArB | Project Facilitator shall email the WG-approved PSS to: - TSC Project Manager (TSC PM) - HL7 Project Management Office (pmo@hl7.org) | WG-approved PSS emailed to TSC and PMO. |

Step 4:  PMO enters the Project Scope Statement into Project Insight (this occurs simultaneously with step 5).

| If the Project’s Sponsor is a… | Actions | Deliverables |
| --- | --- | --- |
| TSC Work Group (most projects fall into this area) Includes ArB. | PMO shall review the WG-approved PSS and direct questions / concerns to the Project Facilitator. The primary review of the PSS by the PMO is to insure the PSS is filled out completely. The Project Facilitator shall resolve any questions/concerns brought forth by the PMO. If updates are necessary to the PSS, the Project Facilitator shall provide an updated PSS to the following: - The sponsoring and co-sponsoring Work Group - The Steering Division The PMO shall enter the PSS into Project Insight; note that this can occur prior to “leader group” (e.g. SD or EC) approval. | WG-approved PSS added to Project Insight. Project Insight assigns a unique Project ID. |
| ArB | Same as above. | Same as above. |

Step 5:  “Leader” Group reviews/approves the Project Scope Statement.

Reviews should focus on the following within the PSS:

- is this PSS clear in terms of its scope and deliverable(s)

- is it within the scope of the sponsoring committee

- how is it related to other projects

- how is it related to the activities of other committees

PSS approvals are typically done via conference calls.  However, if desired, the approval can be through email or a poll (say, a Doodle Poll via www.doodle.com), if the Work Group, Committee, or Council has defined an e-Vote process in their Decision Making Practices.  When doing this, include the URL to the Doodle poll and indicate a deadline date for the review and approval within the email requesting review/approval.

| If the Project’s Sponsor is a… | Actions | Deliverables |
| --- | --- | --- |
| TSC Work Group (most projects are in this area) ArB – see below | The Steering Division shall review the PSS and direct any questions / concerns to the Project Facilitator. | PSS reviewed by the SD. |
|  | The Project Facilitator should attend the Steering Division conference call which has the PSS review on it’s agenda | Project Facilitator attends SD conference call. |
|  | The Project Facilitator shall resolve any questions/concerns brought forth by the Steering Division. If updates are necessary to the PSS, the Project Facilitator shall provide an updated PSS to the following: - The sponsoring and co-sponsoring Work Group - The Steering Division - The PMO Note: Based on the updates, it may be necessary for the PSS to go through Work Group review/approval again. However, "minor" changes can be agreed on-the-spot without a cycle-back to the Work Group. | Resolutions to questions/concerns and update PSS if needed. Provide the WG, SD, and PMO with an updated PSS. |
|  | Upon approval, the SD co-chair or SD PF shall notify the TSC Project Manager (TSC PM) and PMO of the approval. This can be done via SD meeting minutes as both the TSC PM and PMO are subscribers to all SD Listservs. The PMO shall update Project Insight with the approval date. | PSS approved by the SD. Project Insight updated. |
| ArB | Not applicable. | Not applicable. |

Step 6:  Submit Project Scope Statement to TSC for review and / or approval

Reviews should focus on the following within the PSS:

- is this PSS clear in terms of its scope and deliverable(s)

- is it within the scope of the sponsoring committee

- how is it related to other projects

- how is it related to the activities of other committees

PSS approvals are typically done via conference calls.  However, if desired, the approval can be through email or a poll (say, a Doodle Poll via www.doodle.com), if the Work Group, Committee, or Council has defined an e-Vote process in their Decision Making Practices.  When doing this, include the URL to the Doodle poll and indicate a deadline date for the review and approval within the email requesting review/approval.

| If the Project’s Sponsor is a… | Actions | Deliverables |
| --- | --- | --- |
| TSC Work Group (most projects fall into this area) Includes ArB. | The TSC Project Manager (TSC PM) shall - Create a GForge Tracker requesting SD-approved PSS review/approval by the TSC - Add the review to a TSC conference call agenda - Email the SD-approved PSS to WG co-chairs and International Affiliates; include the Project Facilitator as a ‘cc’ in this email. | GForge Tracker created |
|  | The TSC shall review the SD-approved PSS and direct any questions / concerns to the Project Facilitator. | PSS reviewed by the TSC |
|  | The Project Facilitator should attend the TSC Conference Call which has the PSS review on it’s agenda | Project Facilitator attends TSC Conference Call. |
|  | the TSC shall make a determination as prescribed in the GOM Section 09.01, part (d) for projects containing a deliverable that will be a publically available document (for example a government mandated or funded specification, or otherwise subsidized publication). | TSC follows GOM Section 09.01, part (d) for public documents. |
|  | The Project Facilitator shall resolve any questions/concerns brought forth by the TSC. If updates are necessary to the PSS, the Project Facilitator shall provide an updated PSS to the following: - The sponsoring and co-sponsoring Work Group - Their Steering Division - The PMO Note: Based on the updates, it may be necessary for the PSS to go through Work Group and Steering Division review/approvals again. However, "minor" changes can be agreed on-the-spot without a cycle-back to the Work Group and Steering Division. | Resolutions to questions/concerns and update PSS if needed. Provide the WG, SD, TSC and PMO with an updated PSS. |
|  | Upon approval, TSC PM shall communicate the approval via the weekly TSC update email sent to the co-chair and International Affiliates listserv. The TSC PM shall close the GForge Tracker. The PMO shall update Project Insight with the approval date. | PSS approved by the TSC HL7 members notified. GForge Tracker closed. Project Insight updated with TSC approval date and other modifications. |
| ArB | Same as above. | Same as above. |

Step 7:  The HL7 PMO and Project Services Committee insure that HL7 project methodology is adhered to.

NOTE: No definable actions are documented; Project Facilitators are encouraged to attend the ‘Open Forum’ session held at the beginning of every Project Services Work Group conference call if they have any issues to discuss, as well as the Project Facilitator lunch meeting at WGMs.  Upcoming calls can be viewed via the Project Services Work Group page on www.HL7.org.

# FAQ – Frequently Asked Questions

## How do I search/view HL7 Projects?

There are three ways to view HL7 projects, all located at www.HL7.org > Participate > Tools and Resources > Project Tracking Tools

(http://www.hl7.org/participate/toolsandresources.cfm):

- The Searchable Project Database (http://www.hl7.org/special/Committees/projman/searchableProjectIndex.cfm, located on the www.HL7.org Homepage and titled ‘Search current projects from Project Insight)

- An Excel spreadsheet of all HL7 projects is available via GForge > TSC File tab (http://gforge.hl7.org/gf/).

- Project Insight (a Project Insight User ID and Password is required – this differs from your HL7 User ID and Password).  Contact the HL7 PMO for more information (pmo@hl7.org).  The URL is: http://healthlevelseven.projectinsight.net/l.aspx?ReturnUrl=%2fdefault.aspx.

## Where can I find the Project Scope Statement Template?

The most recent version of the Project Scope Statement Template (MS Word document) is located at www.HL7.org > Participate > Templates (http://www.hl7.org/participate/templates.cfm).

## Who is the project facilitator?

The Project Facilitator named in the Project Scope Statement serves as the Project Lead; the 'go to' person for the project who can answer questions regarding status, scope, objectives, issues, risks, etc. regarding the project.

## How do I know the approval status of my project?

Look up your project using the Searchable Project Database (http://www.hl7.org/special/Committees/projman/searchableProjectIndex.cfm), located on the www.HL7.org Homepage).  The search results will reflect SD and TSC approval statuses either by reflecting the date the group approved the project or indicated ‘Awaiting Approval’ if the group has not approved the project.

## Where can I find the list of Steering Division Leaders or Steering Division Project Facilitators?

- Current Steering Division leaders can be found via their Steering Division webpage at http://www.hl7.org/Special/committees/index.cfm.
- Current Steering Division Project Facilitators can be found via a PDF file at www.HL7.org > About > People and Organizations > HL7 Facilitators (http://www.hl7.org/About/hl7facilitators.cfm).

## I’ve submitted my PSS to my Steering Division for approval but haven’t heard anything from them.  What should I do?

First, check the Steering Division’s meeting minutes.  Look to see if your project was on one of their agendas, and if so, if it was approved or the SD had further questions.  Your first point of contact with the SD should be their Project Facilitator.  If you can’t contact them, contact the Steering Division Leaders.

If the SD has approved your project, they will submit it to the TSC for approval via GForge’s tracker system.  To view which approvals your project has gathered, find your project by using the Searchable Project Database (http://www.hl7.org/special/Committees/projman/searchableProjectIndex.cfm), located on the www.HL7.org Homepage).

## The scope or objective of my project changed.  Do I need to create a new PSS?

You may or may not have to as it depends on the change. Oftentimes, the scope or objectives of a project may change during its lifecycle, perhaps due to regulatory changes or tying back to a different standard.

If the change in scope or objectives is minor, simply update the existing project scope statement, and within Project Insight, indicate the modifications in the appropriate fields.  You can also use the ‘Misc. Notes’ text box for documentation.

Best practice:  Use Microsoft Word’s ‘Track Changes’ tool to highlight the changes being made to the Project Scope Statement.

If the change in scope or objectives is major, the Project Facilitator should submit a new Project Scope Statement, as much of the original information won’t accurately reflect what is being done anymore.

## What approvals are needed if I revise my existing PSS, say the project’s scope changes?

The same approval process should be followed whether it’s a new project or a scope change to an existing project.

When the scope is changed in a project, an adjusted or new Project Scope Statement will be approved by the primary WG and the SD, providing the TSC using the same time line and deadlines as submissions for new projects.   
Best practice:  Use Microsoft Word’s ‘Track Changes’ tool to highlight the changes being made to the Project Scope Statement.

## What ballot types are required to go through the project approval process?

All ballot types (Comment Only, Informative, Normative, DSTU) need to go through the project approval process, however, as identified in the Project Scope Statement, a single project can define ballot plans for multiple types of ballots for the project, for example, Comment Only >DSTU > Normative or Informative > Normative.

## When withdrawing or reaffirming a standard, does a PSS need to be created and go through the review/approval process?

Yes, for both cases.  For this question, ‘withdrawing a standard’ refers to many things, such as choosing not to extend a standard that has reached its 5 year end-of-life or identifying the need to sunset a standard.  By creating a PSS and following the approval process, you give the opportunity to communicate the withdrawal to the HL7 membership and allow them to weigh in on any potential work needed to successfully withdraw the standard.

GOM Section 14.13 has more information on withdrawing a standard.

## Do I need to go through the project approval process if a standard has expired and will not be reaffirmed?

When a work group has balloted a standard at DSTU, informative, or normative ballot, and decides the standard will be withdrawn, the withdrawal form at http://www.hl7.org/documentcenter/public/membership/ANSI_proposal_withdrawal.doc is needed for ANSI notification and must be approved by the Work Group and the TSC.

## Do I need to update the PSS if I discover after it’s approved that I need to coordinate ballots with other HL7 Work Groups?

Yes, we recommend updating the Ballot Strategy section of the Project Scope Statement as well as Project Insight.  Include the ballot name and release/version your project is coordinating with.

## What is the approval process for HL7 projects that collaborate with ISO or the JIC?

Follow the process documented on via www.HL7.org > Participate > Balloting > HL7's Collaboration with ISO and JIC (http://www.hl7.org/participate/isojic.cfm).

## How should a Work Group document the voting results after seeking approval for the PSS?

The ideal way is to post it in meeting minutes, so that they are documented and easily referenced.  If that’s not possible, an email to the Listserv will suffice.