## Strategic Plan
| Sep 2011 |  | Jan 2012 |  | May 2012 |  | Sep 2012 |  | Jan 2013 |  | May 2013 |  | Sep 2013 |  | Jan 2014 |  | May 2014 |  | Sep 2014 |  | Jan 2015
| Ballot | WGM | Ballot | WGM | Ballot | WGM | Ballot | WGM | Ballot | WGM | Ballot | WGM | Ballot | WGM | Ballot | WGM | Ballot | WGM | Ballot | WGM | Ballot | WGM
Structured report category
IHE White Paper -- Anatomic Pathology Structured Reporting |  | X |  | X |  | X |  | X |  | X
Implementation Guide with sample CDAs for Anatomic Pathology Structured Reporting |  | X |  | X |  | X | ? | X |  | X
Collaborating with HL7 Structured Documents and HL7 Vocabulary Work Groups in identifying CDA features needed for Anatomic Pathology Reports for addition to CDA Release 3 |  | X |  | X |  | X |  | X |  | X
Specimen Tracking Category
NAACR/CPAC Specimen/divided specimen tracking through multiple performing labs | [5 empty] | ?
Unique Specimen ID Requirements (Informative) - Project |  | X |  | X |  | X | X | X |  | X |  | X | X | X
Unique Specimen ID Requirements (DSTU/Normative) - Project |  | X |  | X |  | X | X | X |  | X |  | X |  | X |  | X |  | X | X | X
ARPH / IHE / NAACCR project
Integration Profile for NAACCR/IHE Anatomic Pathology Cancer Reporting to Public Health |  | X |  | X |  | X |  |  | ? | X
Middleware/Automaton
Look at histology middleware | [5 empty] | ?
Report Display Standards
Look at possible display/GUI standards - tentative | [5 empty] | ?
Tissue Banking
Identify resources for further investigation
?
Tentative
Confirmed
Projected
d
Note on A7: David Booker: Will need to decide how to disseminate to HL7 and publish
Note on A16: David Booker: January 2010 IHE Connectathon in Chicago to be followed by change profiles from vendors. NAACR timeline is consistent with this timeline.