<Insert Project ID >

Laboratory Result-based Adverse Event Assessment

Messaging Specification

Project Charter

July 31, 2007

Version 0.7

TABLE OF CONTENTS

1.0	Revision History	1

2.0	Project Overview / Description	2

2.1	Strategic Fit	2

2.1.1	HL7 Strategic Imperative	2

2.1.2	Project Mandate	2

2.2	Completion and Success Criteria:	2

2.2.1	We have reached completion when:	2

2.2.2	We have achieved success when:	2

2.2.3	Who gets to vote on completion and success?	2

3.0	Project Scope	3

3.1	Scope Inclusions	3

3.2	Scope Exclusions	3

4.0	Project Goals, Objectives and Deliverables	5

5.0	Project Stakeholders, Participants and Resources	5

5.1	Leadership Team	5

5.2	Active Participants & Required Resources	6

6.0	Project Assumptions and Constraints	7

6.1	Project Assumptions	7

6.2	Project Constraints	7

7.0	Project Risks	7

7.1	Project Risks	7

8.0	Preliminary Project Plan	8

8.1	Project Plan/Schedule	8

9.0	Inter-Project Dependencies	9

10.0	Charter Acceptance/ Approvals	9

| Project Id Laboratory Result-based Adverse Event Assessment Messaging Specification |  |
| --- | --- |
| Project Sponsor: | RCRIM Technical Committee |
| Responsible Party: | RCRIM |
| Technical Committee: | RCRIM |
| Project Leader / Manager: Project Co-Leader / Manager: | Phil Pochon Jennifer Neat (City of Hope) |
| HL7 Facilitator: | Abdul-Malik Shakir |

# Revision History

| ###### File Name |  | ProjectCharter_LabResultBasedAEAssmt.doc |  |
| --- | --- | --- | --- |
| ###### Version | Date | Author | Description |
| 0.1 | 06/06/2007 | JL Neat | Initial draft |
| 0.2 | 06/19/2007 | JL Neat | Updated draft |
| 0.3 | 06/19/2007 | JL Neat | Internal review, City of Hope |
| 0.4 | 6/20/2007 | JL Neat | Review with Phil Pochon |
| 0.5 | 6/29/2007 | JL Neat | Review with RCRIM TC - Update Scope Inclusions |
| 0.6 | 7/07/2007 | JL Neat | Review with Project working group - Update Scope Inclusions - Update Scope Exclusions |
| 0.7 | 8/01/2007 | JL Neat | - Added Figure 1 – Sec 3.0 - Update Project Plan/Schedule – Sec 8.1 |

# Project Overview / Description

## Strategic Fit

### HL7 Strategic Imperative

This project supports HL7’s mission to create standards for the exchange, management and integration of electronic healthcare information.  It is directly linked to the HL7 Strategic objective to collaborate with healthcare information technology users to ensure that HL7 standards meet real-world requirements, and that appropriate standards development efforts are initiated by HL7 to meet emergent requirements

### Project Mandate

The mandate of this project is to establish an HL7 v3 messaging draft standard for trial use to facilitate transmission of initial laboratory result-based (lab-based) adverse event (AE) assessment information between an automated lab-based quantitative AE detection and grading service and a system within the local clinical research environment, such as a Clinical Trials Management System (CTMS) or a Clinical Information System (CIS).

## Completion and Success Criteria:

### We have reached completion when:

Project completion will be indicated when the following criteria have been met:

- Project deliverables have been vetted with and approved by subject matter experts in the adverse event domain

- Project risks have been mitigated or the contingency action has been implemented

- Negative ballots have been reconciled

### We have achieved success when:

The project will be considered successful when a messaging specification appropriate for transmitting initial lab-based AE assessment information has been approved as a draft standard for trial use.

### Who gets to vote on completion and success?

The RCRIM Technical Committee as the sponsoring committee for this project is solely responsible for evaluating the completion and success of this project.

# Project Scope

This section specifies the included and excluded activities for this project.  Figure 1 presents an activity diagram depicting a high-level view of the life cycle of a lab-based quantitative adverse event and identifies the boundaries of this project.

## Scope Inclusions

The scope of this project includes:

- Developing specifications to support messaging requirements for initial lab-based AE assessment information, resulting from the automated detection and grading of laboratory test results subject to quantitative AE assessment.

  - Defining the initial message structure and its content. The message content represents a first-level of lab-based quantitative AE assessment only and does not support the findings of the subsequent AE investigation conducted within the local clinical research environment to determine, in part, reporting requirements established by entities such as the protocol sponsor, the oversight committee, and/or regulatory agency.

  - Defining the system interaction(s)/message exchange. The messaging interaction is intended to only facilitate communication between an automated lab-based quantitative AE detection and grading service and a system within the local research environment such as a CTMS or CIS.

- Evaluating the CT Laboratory Message DSTU (PORT_RM030001) and the ICSR Message to determine the appropriate structure for the lab-based quantitative AE assessment messaging specifications.

- Registering the Common Terminology Criteria for Adverse Events (CTCAE v3) as a code system.

- Producing an Implementation Guide for the lab-based quantitative AE assessment CMET

## Scope Exclusions

The scope of this project does not include:

- Developing messaging specifications for AE assessment information pertaining to observations other than laboratory test results subject to quantitative AE assessment.

- Developing messaging specifications to support the investigative findings conducted in response to the initial lab-based quantitative AE assessment.

- Developing specifications to support message exchange between a lab-based quantitative AE detection and grading service and any such entity as a protocol sponsor, oversight committee or regulatory agency.

- Developing specifications for inclusion of a lab-based quantitative AE assessment CMET in message structures other than the CT Lab Message.

Figure 1: Life Cycle of Lab-based Quantitative Adverse Event

# Project Goals, Objectives and Deliverables

| Goals | Objectives | Deliverables | Measure of Deliverable Completion |
| --- | --- | --- | --- |
| Adopt or define an appropriate message for transporting data about initial lab-based quantitative AE assessments | Document the specifications for transporting the initial assessment data between a lab-based quantitative AE grading service and a CIS or CTMS | Storyboard | Vetted with and approved by AE subject matter experts |
|  |  | Activity Diagram |  |
|  |  | Domain analysis model |  |
|  |  | Business Rules |  |
| Harmonize domain analysis model with BRIDG | Adopt existing concepts and/or contribute new concepts specific to laboratory test result and quantitative AE data. | Harmonized domain analysis model | Consensus among AE domain experts contributing to/participating in harmonization efforts across domain analysis models. |
|  |  | Harmonized domain glossary |  |
| Define a CMET for data about initial lab-based quantitative AE assessments | Produce a design specification that could be an optional structure within an existing message structure | RMIM | Vetted with and approved by subject matter experts in the AE and clinical laboratory domains, as well as with the RCRIM technical committee. |
|  |  | HMD |  |
|  |  | Implementation Guide |  |

# Project Stakeholders, Participants and Resources

## Leadership Team

Project Sponsor – RCRIM Technical Committee

Responsible Party - RCRIM

Technical Committee – RCRIM

HL7 Facilitator – Abdul-Malik Shakir

Project Leader / Manager – Phil Pochon

Project Co-Leader, City of Hope (COH) – Jennifer Neat

Beneficiaries – entities needing to communicate data about observation assessments

Project Steering Committee – NA

## Active Participants & Required Resources

| Team Member | Role | Focus Area |
| --- | --- | --- |
| Phil Pochon (PP) | Project leader | CT laboratory data |
| Abdul-Malik Shakir (AMS) | V3.0 methodology facilitator | Design |
| Joyce C Niland (JCN) | Subject matter expert | Analysis |
| Hemant Shah (HS) | Subject matter expert | Analysis & Design |
| Susan Pannoni (SP) | Subject matter expert | Analysis |
| Russ Sarbora (RS) | Subject matter expert | Design |
| Jack Lee (JL) | Subject matter expert | Design |
| Jennifer L Neat (JLN) | Subject matter expert; Project Co-leader, COH | Analysis |

# Project Assumptions and Constraints

## Project Assumptions

- The existing CT Laboratory Message could meet the needs of this project with minimal modification.

- The CMET defined within this project will be applicable to clinical observations other than laboratory.

- No CMET exists as part of the ICSR Message or within the Orders and Observations Domain or the Care Provision Domain that meets this project’s needs. The scope of this project, however, includes soliciting participation of members in these domains and evaluating the ICSR Message to validate this assumption.

## Project Constraints

- This project will not impede the progress of the CT Laboratory Message in transitioning from DSTU to normative status.

# Project Risks

## Project Risks

| Risk Factor Description | Probability of Occurrence (H/M/L) | Severity of Impact (H/M/L) | Risk Strategy/Mitigation Plan | Contingency Action | Anticipated Start – End Date |
| --- | --- | --- | --- | --- | --- |
| BRIDG harmonization schedule | M | H | Frequent communication with BRIDG | Derive domain analysis model from BRIDG | June 2007 August 2007 |
| Scope of the project expanding to exceed the expertise and resources of the project participants | L | M | Require that any scope increment request be accompanied by adequate resources | Implement the project in phases | June 2007 March 2008 |

# Preliminary Project Plan

The project plan and schedule for the Laboratory Result-based Adverse Event Assessment project will be developed and managed using a Gantt Chart.  Section 8.1 provides a high-level summary of the initial project plan.

## Project Plan/Schedule

| Phase, Major Deliverable, Activity or Milestone |  | Responsible | Start Date | End Date |
| --- | --- | --- | --- | --- |
|  | Create Project Charter | Team | June 2007 | June 29, 2007 |
|  | Create storyboard | JL Neat, JL, AMS | June 2007 | June 29, 2007 |
|  | Create BRIDG-derived domain analysis model | Analysis Team | June 2007 | August 2007 |
|  | Evaluate the ICSR RMIM and SDTM model to determine the appropriate structure for the lab-based quantitative AE assessment messaging specification | Analysis Team | June 2007 | July 2007 |
|  | Define a CMET for lab-based quantitative AE assessment | Design Team | July 2007 | July 2007 |
|  | Modify the CT Lab Message | Design Team | Aug 2007 | Aug 2007 |
|  | Solicit participation of members from the Orders and Observations domain and the Care Provision domain | JL Neat | August 2007 | August 2007 |
|  | Register the CTCAE v3 as a code system | Design Team | August 2007 | August 2007 |
|  | Project Update to RCRIM TC | Team | Aug 7, 2007 | Aug 7, 2007 |
|  | Review proposed CT Lab Message changes to the Laboratory Results for Clinical Trials group | Team | August 14, 2007 | August 14, 2007 |
|  | Submit proposed messaging specification to RCRIM TC | Design Team | Sept 4, 2007 (telecom) | Sept 15-21 2007 (WGM) |
|  | Obtain RCRIM approval to go to ballot | Team | Sept 15, 2007 | Sept 21, 2007 |
|  | BRIDG Harmonization | Analysis Team | October 2007 | November 2007 |
|  | Announce Intent to Ballot (deadline is Oct 28) | Team / RCRIM | Oct 28, 2007 | Oct 28, 2007 |
|  | Prepare and submit ballot material (work with Publishing Committee) for Jan 2008 ballot | Team | Nov 1, 2007 | Nov 25, 2007 |
|  | Ballot reconciliation | RCRIM | Jan 17, 2008 | Jan 22, 2008 |
|  | Create Implementation Guide | Team | January 2008 | January 2008 |

# Inter-Project Dependencies

Inputs Required: This project requires deliverables from other projects as specified below.

| Area or Predecessor Project | Deliverables Needed as Input | Date Required |
| --- | --- | --- |
| BRIDG | Harmonized BRIDG Model v1.0 | June 15, 2007 |

Outputs to be supplied: This project has a responsibility to provide deliverables to other projects as specified below.

| Area or Successor Project | Deliverables Supplied to Successor | Date Required |
| --- | --- | --- |
| BRIDG | Domain Analysis Model | August 2007 |

# Charter Acceptance/ Approvals

The following approvals indicate acceptance of the project charter.

| Date | Status | Change Approved | Approval Body | Reference to Decision |
| --- | --- | --- | --- | --- |