- Specimen Project Conference Call

- 29 March 2012

- +1 770 657 9270, Passcode: 653212#

- Attendees:

| Name | Organization |
| --- | --- |
| Joyce Hernandez | Merck |
| Jim Case | # NLM |
| Ron van Duyne | CDC |
| Joan Knapp |  |
| Hans Buitendijk | Siemens Healthcare |
| Riki Merrick | IConnect Consulting / APHL |
| Lisa Schick | Scenpro |
| Lorraine Constable (starting at 12:30) | Constable Consulting |

- Co-Chair: Hans Buitendijk

Scribe:  Riki Merrick, Hans Buitendijk

- Agenda/Minutes:

- Agenda Review:

  - Project Statement

  - Use Cases Review and Data Requirements

Approach

- We agreed to follow this sequence with leads listed for each step

  - Review/refine DAM – Joyce Hernandez, Mukesh Sharma

  - Starting point: NCI Life Sciences DAM: Specimen Core.

  - V3 CMET/RMIM compare + updates – Lorraine Constable

  - V2 SPM compare + updates – Riki Merrick, Hans Buitendijk

  - Validate Specimen Identifier format support.

Project Statement

- Suggest to include both V2 and V3

- Rather than marking as informative, DSTU, seems a better idea to split in order to get clear deadlines.

- Need to have

  - Specimen DAM (new)

  - Specimen CMET (existing one updated) focus on V3 – DSTU

  - Specimen CMET Normative

  - V2.x for any V2 related updates (covered through general V2.x project)

- Other groups – to co-sponsor: PHER?, if not interested for sure, as is RCRIM

- Do we need a different modeling facilitators between DAM and CMET project? No

- There is no need for implementers for DAM, so CMET project only where we need to specify that.

- Write DAM description / scope and success  – see updated doc

- Timelines:

  - Due date to refine DAM: Jan 2013

  - CMET due date: Sep 2013

  - V2.x is dependent on that timeline

  - Normative way after that – just leave as separate project – or aim for 1 year after DAM, i.e. sept 2014 at the earliest – make separate PSS.

- No need for formal SDO agreements needed.

- Lorraine assumed DAM was covered under Clinical Genomics – that would require to change that project to OO – creating a new one would be easier.

- Hans / Lorraine will update for review next call.

- Need detail use cases and collect data requirements and then do gap analysis to core model

- Wiki page for specimen project:

  - Need to fix the link to the clinical genomics use case

  - Add the research use case:

  - Need to add html version of specimen core DAM is on specimen project wiki – Lisa will do that