## Sheet1
Number | priority | Issue | Section | Existing Wording | Proposed Wording | Comments | proposed Disposition | Status
1 | 3 | CWE/CNE elements |  |  |  | Should the many of the CWEs be CNE since we bind the Vocabulary to the value set attibrute? | brought up for discussion in OO for context on why is way it is currently. Check with CGIT to see if OK to Constrain from CWE to CNE and will consider for all CWE in S&I guides. | Open
2 | 1 | Source of truth for Value sets | 5.1.5 |  |  | PHINVADs vs HL7 or SDO. | recommended remove phinvads and unless primary source, for rcmt should vs shall and loinc shall. | Open
3 | 1 | Review guidance sections | 7 |  |  | need to edit, keep, remove
4 | 1 | OBX following SPM or OBX following "Epi OBR" |  |  |  | Where to put AOE observations. After SPM? Bad precendent is this conflating patient demographics with Specimen. 21.1.2 General question about why it matters where the OBX lives. – just query OBX.3 to determine where it belongs. Bind the epi questions VS so can route the data properly? Simplify usage for sender ( conformance tester ;) ) never know which context the OBX is in - they should have a context identifier ( OBX.OBR OBX.SPM OBX.PID OR OBX, SBX, PBX - topic for 2.9?) If they can send with test observation. Ideally would like to make OBX following the SPM – but can’t do that and maintain backwards compatibilty
5 | 1 | AOE observations. Do they belong (see 4) | 7.9
6 | 1 | NullFlavors for OBX.5 coded elements | 4.11.1 |  |  | Need to consider same for OBX.5 SCT or NullValue ***this is more difficult -for OBX.2 = CWE can bind to limited set of qualifiers, findings and all of organisms. And then what about AOE Preg ( YNU )
7 | 1 | paired serology |  |  |  | need to increase cardinality of SPM | bring up for discussion in OO for example.
8 | 2 | Do we want to support CE Datatype for OBX.5 | 2.1
9 | 1 | LRI defers to base standard on Lengths - Does ELR want to follow |  |  |  | Will need to to create a thin LRI-profile. | bring up for discussion in OO for example after research this first.
10 | 3 | Change Patient group cardinality and ORC.12 and OBR.16 (ordering provider) from 1..* to 1..1 |  |  |  | this is not backwards compatible but is same as LRI.
11 | 1 | How to handle Specimen Group | 3.1 |  |  | Original conditional didn't work should this be RE or C
12 | 2 | bind SPM.4 to SNOMED CT | 4.12 |  |  | disallow HL70487? No longer backwards compatible?