# Action List

|  |  |  |
| --- | --- | --- |
| **What** | **Who** | **When** |
| Write an intermediate report of IPS activities (Marketing scope) | Kai; Catherine | Before Madrid |
| HL7 and CEN should have mutual references in their deliverables. TS document will include direct reference of the HL7 IPS IG | All |  |
| Provide feedback about the CEN HL7 agreement (Oslo statement) | Whyne |  |
| Give access to the prEN and prTS documents to the HL7 community for comments | Steve |  |
| HL7 community comment the prEN and prTS documents | All |  |
| Set up a meeting with SDWG in Madrid | Rob |  |
| Explore the possibility of a meeting with eHDSI representatives in Madrid. Scope to be clarified | Catherine / Christof |  |
| Organize periodic reports for WGs (see below) | All |  |

|  |  |  |
| --- | --- | --- |
| **What** | **Who** | **When** |
| Patient Care, send an email with the summary | Rob |  |
| Templates (covered) |  | done |
| Emergency Care, send an email with the summary.  | Rob |  |
| Vocabulary (Rob) | Rob |  |
| Electronic Health Records (covered) | === | done |
| HL7 International Council, ask for a presentation in Thursday 10 minute: write to Melva. | Giorgio |  |
| Healthcare Standards Integration, send an email with the summary | Rob |  |

|  |  |  |
| --- | --- | --- |
| **What** | **Who** | **When** |
| Organize a Meeting with Pharmacy (and RCRIM). To be defined the topic to be discussed. | Kai | Before Madrid |
| Organize at least an additional Quarter  | All |  |
| Organize at telephone conference with EMA representatives about strategies about how to leverage IDMP in the IPS related projects. | Christof |  |

| **What** | **Who** | **When** |
| --- | --- | --- |
| Set up a mediaWiki editorial environment | Kai | Next week |
| Load the IG TOC | Kai | Next week |
| Refine the TOC and expand the content |  |  |
| Assign editorial tasks | All |  |
| Prepare the front pages | Giorgio |  |
| Prepare a stylesheet for the pdf export | Kai |  |
| Investigate with HL7 HQ the use of the HL7 Int. pub wiki | Kai | Madrid |
| Create Examples of usage of known absent and unknown cases for the different sections  | All |  |
| Contact SNOMED CT for asking about strategies on EDQM and substances (IDMP) | Rob |  |
| Check the feasibility of taking advantage of the cooperation in Trillium II with SNOMED CT International about mapping and value set for the IPS | Catherine |  |
| Discuss medical devices |  |  |
| Section deep dive: Other sections * Functional Status (Autonomy/Invalidity)
* Plan of care
* Social History
* Pregnancy (expected day of delivery)
* Advance Directive
 |  |  |
| Complete the discussion about* Provenance
	+ Human curated
	+ Automatic
	+ Unknown
	+ Mixed
* Identification of the “type of Patient Summary”:
	+ Single vs Multi Encounter;
	+ Single vs Multi organization;
	+ clinical act VS automatic collection VS mixed mode (see also provenance)
 |  |  |
| Analyze the header |  |  |
| Creation of a HL7 International extension for SNOMED CT | Rob |  |
| Update the list of concept in the IPS no info section wiki page (Known absent…) | François |  |
| Update the Allergy section according to the agreed changes | Giorgio |  |
| Continue the evaluation of the optional Alert section. May have a reference to problem , allergy or stand on its own code or textual description. | All |  |
| Update the Problem List section according to the agreed changes | Giorgio |  |
| Prepare the list of Value Set based on SNOMED CT to be submitted to HTA for being included in the list of free value sets. | All |  |
| Communicate the value set we’d like to use to HTA | Rob |  |
| Ask to Stephen Chu the status of the problem status value set | Giorgio |  |
| Create history of procedure section and include the agreed decisions | ??? |  |
| Change all the ACT IDs from 1..\* to 0…\*  | Kai |  |
| Add example of usage of TS in the SBADM effective time | Giorgio |  |
| Share the presentation about immunization  | Kai |  |
| Update the immunization section according to the agreed decisions | Kai |  |
| Update (some ?) CD, CE with the epSOS constraints  | Giorgio ? Kai ? |  |
| Remove all the constraints on II  | Giorgio ? Kai ? |  |
| Update the Result templates as agreed | François |  |
| Update the Medications templates as agreed | Giorgio |  |

| **What** | **Who** | **When** |
| --- | --- | --- |
| Start the discussion on the header | All |  |
| Load a first header template on ART DECOR | TBD |  |
| Include the discussion about the Care Plan section in the first call if April. Talk with Stephen | Rob |  |