Meeting Minutes

CDISC-HL7 Stage II

November 5, 2008

12:00 am – 2:00 pm (EST)

Attendees / Affiliation

Jason Rock/Global Submit (Chair)

Patty Garvey/FDA (Facilitator)

Scott Getzin/Eli Lilly

Marcelina Hungria/Image Solutions

Joyce Hernandez/Merck

Wayne Kubick/Lincoln Technologies

Mary Lenzen/Octagon

Jay Levine/FDA

Armando Oliva/FDA

Mitra Rocca/Novartis

Chris Tolk/CDISC

Clyde Ulmer/NCTR

Diane Wold/GSK

Background

FDA wishes to receive, in regulatory submissions, standard clinical study information content developed by the Clinical Data Interchange Standards Consortium (CDISC) in a Health Level 7 (HL7) message exchange format.  This is key to the FDA strategic initiatives to improve public health and patient safety.

This project is currently broken into two stages: requirements analysis and message development.  Stage IB team was developed and tasked with the requirements analysis responsibilities.  Stage II team was developed and tasked with the message development responsibilities.

The purpose of the meeting is to discuss mapping of selected SDTM domains (demographics, deposition, exposure, adverse event, and laboratory) to the Study Design and HL7 clinical statement and review the ballot comments for StudyParticipation and StudyDesign from DSTU September 2008 ballot cycle.

Discussion

- The October 22, 2008 meeting minutes were reviewed and approved.

- The Study Participation DSTU will be re-balloted for the January 2009 meeting in Orlando.

The Study Design and Trial Use will be balloted as an informative ballot with the May 2009 cycle. Study Design is not ready for normative ballot yet. There are some comments that we don’t know how to address and a DAM is needed. By making this an informative ballot we are not required to answer all comments. Until outstanding comments already received are resolved it does not make sense to re-ballot and get the same comments again.

- Jason will be meeting with Lise Stevens next week at ICH meeting. They will try to work in the mapping of the AE Domain and will share with this group the results.

- LAB:

  - LBDY – In order to calculate LBDY, RFSTDTC need to be defined in Demo. Study Design need to define RDSTDTC and how the definition could be machine readable. This was flagged (red) as a gap.

  - The mapping of SDTM Labs (LB) to HL7 Study Participation RMIM classes was completed and documented in the spreadsheet.

- The next regularly scheduled Stage II meeting on November 19 has been reschedule for Wednesday, November 26 at 11:00pm to 1:00pm (EST).

- The team started to review ballot comments received from Diane Wold. Comments were added to the spreadsheet.

ACTION ITEMS:

- Jason to discuss with HL7 headquarters comments that we are not able to address.

- Jason will compile a list of gaps from the lab spreadsheet.

Attachments: 	(1) SDTM domains mapping

(2) Updated comments document

Drafted: C. Tolk/11-5-2008

Approved: 12-10-2008